VOLUME 2

# SECTION 3:
SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement, if necessary, the General Conditions governing the contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions. Other Special Conditions should be indicated afterwards. Note that the Special Conditions must not derogate to the General Conditions where such derogations are not provided for by the General Conditions without the prior approval (derogation) of the relevant services of the European Commission. Please remember to delete this paragraph and all such brackets in the final version of the Special Conditions.

- Article 2: 	Law and language of the contract

2.1	Community law is the law which applies to the contract, complemented, where necessary, by Belgian law.

2.3	The language used shall be English.

- Article 3: 	Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

(a) the contract,

(b) the Special Conditions,

(c) the General Conditions,

(d) the technical specifications,

(e) the design documentation (drawings),

(f) the price breakdown,

(g) the tender with the appendix,

(h) any other document forming part of the contract.

- Article 4:	Communications

For the Contracting Authority

| Name: | Delegation of the European Commission to the Republic of Serbia |
| --- | --- |
| Address: | GTC 19 Avenue Building, Vladimira Popovica 40, 11070 Belgrade, Serbia |
| Telephone: | Tel.: +381 11 3083 200 |
| Fax: | Fax.: +381 11 3083 201 |
| e-mail: | Delegation-serbia@ec.europa.eu |

For the Contracting Authority’s Representative

| Name: | Mr Josep Lloveras, Head of Delegation |
| --- | --- |
| Address: | GTC 19 Avenue Building, Vladimira Popovica 40, 11070 Belgrade, Serbia |
| Telephone: | Tel.: +381 11 3083 200 |
| Fax: | Fax.: +381 11 3083 201 |
| e-mail: | Delegation-serbia@ec.europa.eu |

For the Beneficiary

| Name: | Biljanovski Djordji |
| --- | --- |
| Address: | Serbia, 11500 Obrenovac, TENT Bogoljuba Urosevica - Crnog 44 |
| Telephone: | + 381 11 8755 003 |
| Fax: | + 381 11 8755 500 |
| e-mail: | djordji.biljanovski@tent.rs |

For the Supervisor:

| Name: |  |
| --- | --- |
| Address: |  |
| Telephone: |  |
| Fax: |  |
| e-mail: |  |

For the Works Contractor.

| Name: |  |
| --- | --- |
| Address: |  |
| Telephone: |  |
| Fax: |  |
| e-mail: |  |

4.1	All communications shall be written (hard copy) and delivered either by:

1) Safe hand to the office of the other party

2) Private courier service

3) E-mail

4) Fax

Where signed documents are transmitted electronically they shall be confirmed by  delivery of hard copy with the original signatures within one week.

- Article 5:	Supervisor and Supervisor's representative

5.2 	Office accommodation for the Supervisor will be provided by the Beneficiary, EPS.

5.3 	The Supervisor acts for the Contracting Authority. He has no authority to relieve either party of any duties, obligations or responsibilities under the Contract. Any approval, check, certificate, consent, examination, inspection, instruction, notice, proposal, request, test, or similar act by the Supervisor (including absence or disapproval) shall not relieve the Contractor from any responsibility he has under the Contract, including the responsibility for errors, omissions, discrepancies and non-compliances.

Any failure to disapprove any work, plant or materials shall not constitute approval, and shall therefore not prejudice the right of the Supervisor to reject the work, plant or materials.

The Supervisor may issue to the Contractor (at any time) instructions which may be necessary for the execution of the works and the remedying of any defects, all in accordance with the Contract. The Contractor shall only take instructions from the Supervisor. If an instruction constitutes a modification, Article 37 of General Conditions shall apply.

The Supervisor shall consult with each party in an endeavour to reach agreement. If agreement is not achieved, the Supervisor shall make a fair determination in accordance with the Contract, taking due regard of all relevant circumstances.

During the design stage Supervisor shall be entitled to perform checks on Contractor progress as well as compliance with Technical Specification. These checks shall be performed at least once in two weeks and Supervisor shall have right to ask for clarification, to approve or reject proposed design solution. Except for changes that are result of Contracting Authority’s on the bases of Beneficiary Request additional orders, Contractor shall not be entitled to any additional costs and/or extension of time, which may occur as result of clarification or rejection of the part or whole of design.

The Beneficiary shall monitor the Project according to Volume 3 and  the approved Time Shedule.

5.4 	Administrative orders issued by the Supervisor shall be dated, numbered and entered in a register. The Supervisor shall send them electronically (by email) to representatives of the Contractor, of the Beneficiary and of the Contracting Authority. Hard copies shall be delivered by hand to representatives of the Contractor and of the Beneficiary, and where appropriate, also to the representative of the Contracting Authority.

- Article 7:	Sub-contracting

Subcontracting is allowed up to 50% of the value of the Contract Works.

- Article 8:	Documents to be provided

On the basis of the

- Inspection Report of the EsP equipment at TENT A Power Plant, Unit A6, and

- Inspection Report of the EsP equipment at TENT B Power Plant, Unit B2,

provided by the Contracting Authority,

- Data collection at site,

- Ash resistivity measurement,

- Particles size measurement,

done by the Contractor on site, he shall produce

- Flue Gas Computational fluid Model (CFD),

- Basic Design, and

- Detailed Design.

The Contractor's Documents shall comprise the technical documents specified in the Technical Requirements, documents required to satisfy all regulatory approvals.

The Contractor shall prepare all Contractors’ Documents, and shall also prepare any other documents necessary to instruct the Contractor's Personnel. The Beneficiary's Personnel shall have the right to inspect the preparation of all these documents, wherever they are being prepared.

- Article 9:	Access to the site

9.1	The Contractor’s attention is drawn to the fact that there is a Head of Delegation of the European Commission in the state of the Contracting Authority. The Contractor is bound to give the Head of Delegation free access to its sites, factories, workshops, etc., and generally assist the Head of Delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the Head of Delegation.

All correspondence between the Contractor and the Contracting Authority or project Supervisor must be copied, for information, to the Head of Delegation of the European Commission at the following official address:

Delegation of the European Commission to the Republic of Serbia

GTC 19 Avenue Building

Vladimira Popovica 40

11070 Belgrade

Serbia

Tel.: +381 11 3083 200

Fax.: +381 11 3083 201

  - Access to site to the Contractor (Article 9.1 of the General Conditions amended):

The Contracting Authority shall, through Beneficiary, in due time and in conformity with the progress of the works, place the site and access thereto at the disposal of the Contractor in accordance with the programme of implementation of tasks referred to in these General Conditions. The Contractor shall afford all reasonable opportunities to other persons concerned for carrying out their work as set out in the Special Conditions or as required by administrative orders.

Period of access to the site will be:

(A6) - 01.05.2010. -30.11.2011.

(B2) - 01.04.2011. - 31.07.2012.

Article 12:	General obligations of the Contractor

12.8	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: http://ec.europa.eu/europeaid/work/visibility/index_en.htm.

Article 12a:	Design and build contracts

The Contractor will produce and be responsible for the Basic Design, the Detailed Design and Flue Gas Computational fluid Model (CFD), with all necessary drawings and calculations, on the basis of the Functional and performance specifications as presented in the Volume 3 of the Tender Dossier (, Technical Requirements), Volume 4 (Breakdown of the Overall Price) and Volume 5 (Design Documents, including Drawings), and on the basis on his own measurements on site. All additional necessary information for this purpose, the Contractor will get from the Beneficiary.

Design(s) shall be prepared by qualified licensed designers who are engineers or other professionals who comply with the criteria stated in the Technical Requirements. Unless otherwise stated in the Contract, the Contractor shall submit to the Supervisor for consent the name and particulars of each proposed designer and design Subcontractor.

The Contractor warrants that he, his designers and design Subcontractors have the experience and capability necessary for the design. The Contractor undertakes that the designers shall be available to attend discussions with the Supervisor at all reasonable times, until the expiry date of the relevant Defects Liability Period.

- The CFD, the Basic Design, and the Detailed Design (in English language) will be submitted to the Supervisor for his inspection and to the Beneficiary. The official inspection and approval of the Detailed Design shall be performed as per the Construction Law of the Republic of Serbia and shall be organized by the Beneficiary.

- Officially approved Detailed Design, by authorities in charge, will be the basis for implementation of works.

- Contractor will produce necessary workshop drawings and As Built Drawings.

Article 14:	Staff

14.1 Add the following paragraph to the article 14.1: All relevant employees must possess the necessary professional licences as required by the Construction law and other relevant legal provisions. Project Manager should have at least 10 years of professional experience, and other Key personnel should have at least 5 years of professional experience.

14.3 Working hours

The Beneficiary will enable access to the site 7 days in the week, 24 hours, for the whole duration of the works.

No work shall be carried out on the Site on locally recognised days of rest, or outside the normal working hours, unless:

the Supervisor gives consent, or

the work is unavoidable, or necessary for the protection of life or property or for the safety of the Works, in which case the Contractor shall immediately advise the Supervisor.

- Article 15:	Performance guarantee

15.1	The amount of the performance guarantee covering liquidated damages for the performance of the works shall be 10% of the amount of the Contract and any addenda thereto.

- Article 16:	Insurance

16.7	The amount of insurance for design is 10% of the Contract amount..

- Article 17:	Programme of implementation of tasks

There are no specific requirements of the programme of implementation of tasks.

- Article 19:	Contractor's drawings

  - Add the following paragraph to the article 19..1:

The Contractor shall prepare, and keep up-to-date, a complete set of "as-built" records of the execution of the Works, showing the exact as-built locations, sizes and details of the work as executed. These records shall be kept on the Site and shall be used exclusively for the purposes of this Sub-Clause. Two copies shall be supplied to the Supervisor prior to the commencement of the Tests on Completion.

In addition, the Contractor shall supply to the Engineer as-built drawings of the Works, showing all Works as executed, and submit them to the Supervisor for review under. The Contractor shall obtain the consent of the Supervisor as to their size, the referencing system, and other relevant details.

Prior to the issue of any Provisional Acceptance, the Contractor shall supply to the Supervisor the specified numbers and types of copies of the relevant as-built drawings, in accordance with the Technical Requirements. The Works shall not be considered to be completed for the purposes of acceptance under Articles 57 to 62 of the General Conditions until the Supervisor has received these documents.

19.7	The language of the manuals and drawings will be English and Serbian.

- Article 20:	Sufficiency of tender prices

Tender prices must cover all necessary design and build activities. No extension of contract is possible.

- Article 21:	Exceptional risks

There are no exceptional risks other than specified in the General Conditions.

Article 24:	Interference with traffic

24.1	There are no interferences on the communication traffic.

24.2	Contractor will have to take necessary measures to secure the transportation of heavy loads and big size loads on and around the site.

- the Contractor shall (as between the Parties) be responsible for any maintenance which may be required for his use of access routes;

- the Contractor shall provide all necessary signs or directions along access routes, and shall obtain any permission which may be required from the relevant authorities for his use of routes, signs and directions;

- the Contracting Authority and the Beneficiary shall not be responsible for any claims which may arise from the use or otherwise of any access route,

- the Contracting Authority and the Beneficiary do not guarantee the suitability or availability of particular access routes, and

- Costs due to non-suitability or non-availability, for the use required by the Contractor, of access routes shall be borne by the Contractor.

For the Transport of Goods:

- the Contractor shall give the Supervisor not less than 7 days' notice of the date on which any Plant or a major item of other Goods will be delivered to the Site;

- the Contractor shall be responsible for packing, loading, transporting, receiving, unloading, storing and protecting all Goods and other things required for the Works; and

- the Contractor shall indemnify and hold the Contracting Authority and the Beneficiary harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from the transport of Goods, and shall negotiate and pay all claims arising from their transport.

- Article 27:	Demolished materials

27.1	No demolition materials will become the property of the Contracting Authority. Should some materials be of interest to the Beneficiary, they will become their property, like metallic scrap.

    - The Contractor will remove demolition materials as per the tables in Volume 4: Table 4.1.2.a and 4.1.2.b, except for the items under the responsibility of the Beneficiary.

- Article 29:	Temporary works

  - Should the Contractor need any additional information or drawings apart from those being part of the Tender Dossier, he will put his request to the Beneficiary. Final decision will be on the side of the Supervisor. Particular temporary works to be performed by the Beneficiary are specified in the tables in Volume 4: Table 4.1.2.a and 4.1.2.b.

- Article 30:	Soil studies

  - No special soil studies are needed apart from what is specified in the Tender Dossier.

- Article 32:	Patents and licenses

  - There is no derogation from Article 32 of the GC.

- Article 34:	Period of implementation of tasks

The identified date for outage by the Beneficiary for project implementation is:

Unit A6: from 01.06.2010 to 31.10.2010,

Unit B2: from 01.05.2011. to 31.07.2011.

- Article 36:	Delays in implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10% of the contract price or, if the contract is subdivided into phases, 10% of the price of the phase concerned.]

- Article 39:	Work register

39.1	Work register is required, and practical details will be specified in the Project Manual provided by the Supervisor subject to approval by the Contracting Authority and the Beneficiary.

39.2	The technical rules for drawing up the statements will be specified in the Project Manual.

- Article 40:	Origin and quality of works and materials

## 40.1	All supplies and material to be incorporated in or required for the works must originate in a Member States of the European Union or in a country or territory of the regions covered and/or authorised by the specific instruments applicable to the IPA 2007 programme under which the contract is financed. For these purposes, "origin" means the place where the materials and/or equipment are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods shall be determined according to the rules laid down in the Community Customs Code or the international agreements to which the country concerned is a signatory.

There are no derogations from the rules of origin.

When importing goods, any change in the specified origin must have been pointed out to the project Supervisor and subject to his approval.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*) the requirements specified in Volume 3 (Technical Requirements).

(*) the specifications as in Volume 5.

40.3	No preliminary technical acceptance is necessary.

- Article 41:	Inspection and testing

The Beneficiary's Personnel shall at all reasonable times:

- have full access to all parts of the Site and to all places from which natural Materials are being obtained, and

- during production, manufacture and construction (at the Site and elsewhere), be entitled to examine, inspect, measure and test the materials and workmanship, and to check the progress of manufacture of Plant and production and manufacture of Materials, on the basis of approved QA & QP.

The Contractor shall give the Beneficiary's Personnel full opportunity to carry out these activities, including providing access, facilities, permissions and safety equipment. No such activity shall relieve the Contractor from any obligation or responsibility.

The following shall apply to all tests specified in the Contract, other than the Tests on Completion:

The Contractor shall provide all apparatus, assistance, documents and other information, electricity, equipment, fuel, consumables, instruments, labour, materials, and suitably qualified and experienced staff, as are necessary to carry out the specified tests efficiently. The Contractor shall agree, with the Supervisor, the time and place for the specified testing of any Plant, Materials and other parts of the Works.

The Supervisor may, under Article 37 [Modifications], vary the location or details of specified tests, or instruct the Contractor to carry out additional tests. If these varied or additional tests show that the tested Plant, Materials or workmanship is not in accordance with the Contract, the cost of carrying out this Modification shall be borne by the Contractor, notwithstanding other provisions of the Contract.

The Supervisor shall give the Contractor not less than 24 hours' notice of the Supervisor 's intention to attend the tests. If the Supervisor does not attend at the time and place agreed, the Contractor may proceed with the tests, unless otherwise instructed by the Supervisor, and the tests shall then be deemed to have been made in the Supervisor 's presence.

- Article 43:	Ownership of plant and materials

43.2	All equipment, temporary works, plant and materials on site owned by the Contractor or by any company in which the Contractor has a controlling interest shall, for the duration of the execution of the works, be made subject to a lien in favour of the Contracting Authority.

- Article 44:	General principles for payments

44.1	Payments shall be made in euro.

44.2	Where invoices are presented to the Contracting Authority, the Contractor shall inform the Commission of the European Communities thereof by sending a copy of the correspondence to  Delegation of the European Commission to the Republic of Serbia, F&C Section

GTC 19 Avenue Building

Vladimira Popovica 40

11070 Belgrade

Serbia

44.3	By derogation the payment to the Contractor of the amounts due under each of the interim payment certificates and the final statement of account issued by the Supervisor shall be made by the Contracting Authority within 45 days.]

- Article 46:	Pre-financing

46.(1) and (2)	Pre-financing shall be granted to the Contractor, at his request, for operations connected with the implementation of the tasks, in the cases if he affords proof of the conclusion of a contract for the purchase or order of materials, plant, equipment, machines and tools, necessary for the execution of the contract, and of any other substantial prior expenses such as the acquisition of patents or study costs.

The pre-financing shall be 20 % of the contract price.

In order to obtain pre-financing payment, the Contractor must forward to the Supervisor the payment request and the performance guarantee in accordance with article 15. The Contractor must provide a financial guarantee for the full amount of the pre-financing payment.

46.8	The repayment of the pre-financing shall take the form of deductions based on claims as per the Annex I: Schedule of payments.

- Article 47:	Retention monies

47.1	When the Final Acceptance Certificate has been issued for the Works, half of the Retention Money shall be certified by the Supervisor for payment to the Contractor.

Promptly after the latest of the expiry dates of the Defects Liability Periods, the outstanding balance of the Retention Money shall be certified by the Supervisor for payment to the Contractor.

However, if any work remains to be executed under Article 61 [Defects Liability] or Article 58 [Tests on Completion], the Supervisor shall be entitled to withhold certification of the estimated cost of this work until it has been executed.

The sum to be retained from interim payments to guarantee implementation of the Contractor's obligations during the maintenance period is10% of each instalment.

- Article 48:	Price revision

  - The contract shall be at fixed prices which shall not be revised.

- Article 49:	Measurement

49.1	This is a lump-sum contract, as per the V4: BREAKDOWN OF THE OVERALL PRICE.

- Article 50:	Interim payments

50.1	Payments will be practically arranged in the following way:

| Payment Milestone | Payment Milestone Date | Delivery Milestones | Milestone Value | Milestone Value as % of Prject Cost |
| --- | --- | --- | --- | --- |
| 1 |  | Advance Payment Contract signed, bank guarantees submitted to the CA. |  | 20% |
| 2 |  | First interim payment Time Schedule, Quality Plan and Main Design approved, Acceptance Certificate issued, Key materials ordered and Overall progress of 30% achieved. |  | 55% |
| 3 |  | Second interim payment Finalized erection of mechanical equipment and all other equipment delivered on site, Overall progress of 80% achieved. |  | 90% |
| 4 |  | Final payment Final Acceptance Certificate issued. |  | 10% |

The amount certified in each Interim Payment Certificate shall be paid by the Contracting Authority against presentation of the Invoice in the amount of Interim Payment Certificate confirmed by the Beneficiary and signed by the Supervisor; the original of the Interim Payment Certificate and original of Statement issued to and approved by the Supervisor.

- Article 51:	Final statement of account

51. (1) and (2)

51.1	The draft final statement of account shall be submitted at the latest at the moment of the Contractor's application for the provisional acceptance certificate.

51.2	The Supervisor shall prepare and sign the final statement of account within 30 days from the issue of the certificate of final acceptance referred to in article 62.

- Article 53:	Delayed payments

53.1	Once the deadline laid down in Article 44.3 of the General Conditions has expired, the Contractor shall receive late-payment interest:

-	at the rate applied by the European Central Bank to its main refinancing transactions in euro where payments are in euro,

-	at the rediscount rate applied by the central bank of the beneficiary country if payments are in the currency of that country,

on the first day of the month in which the deadline expired, plus three and a half percentage points. The late-payment interest shall apply to the time which elapses between the date of the payment deadline, and the date on which the Contracting Authority’s account is debited. By way of exception, when the interest calculated in accordance with this provision is lower than or equal to EUR 200, it shall be paid to the Contractor only upon a demand submitted within two months of receiving late payment. The Member States are not entitled to late-payment interest]

- Article 59:	Partial acceptance

59.3	The maintenance period begins after the date of Final Acceptance Certificate.

- Article 60:	Provisional acceptance

Provisional acceptance means taking control of plant or equipment and presumes that all commissioning checks have taken place except those that require full operational duties. Preliminary acceptance does not imply acceptance for contractual purposes but in order for Units A6 / B2 to return to commercial operation, the Beneficiary will operate the taken over plant to meet it’s requirements, bearing in mind the need to carry out the contractual performance tests.

- Article 61:	Defects liability

- The duration of the Defects Liability period is 365 days.

| Reliability Run The total Contract value will decrease by the percentage specified for every day or part of a day during the Defects Liability Period, during which Units A6 / B2 are out of operation as a direct result of a fault of the Upgrated Electrostatic Precipitation System Main function. | 0.2% of Total Contact Price per day, up to 10%. |
| --- | --- |

61.1	As stated in the glossary of terms in general annexes, the defects liability period is defined as the period stated in the contract immediately following the date of provisional acceptance, during which the Contractor is required to complete the works and to remedy defects or faults as instructed by the Supervisor. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.6 	The defects liability work necessitated by normal wear and tear is to be carried out by the Contractor.

- Article 68:	Dispute settlement

The Sub-article 68.3 of the GC changes and reads: In the absence of an amicable settlement, a Party may notify the other Party in writing requesting a settlement through conciliation by a Dispute-settlement Committee. This Committee shall be appointed within 60 days of any party giving referral of a dispute to the Dispute-settlement Committee. The Committee shall comprise of 1 (one member) to be appointed by International Chamber of Commerce. Rules of the ICC apply, and the language is English.

The other Party shall respond to this request for conciliation within 30 days. Unless the Parties agree otherwise, the maximum time period laid down for reaching a settlement through conciliation shall be 120 days from the notification requesting such a procedure. Should a Party not agree to the other Party's request for conciliation, should a Party not respond in time to that request or should no settlement be reached within the maximum time period, the conciliation procedure is considered to

have failed.

68.4	If the conciliation procedure fails, each Party may refer the dispute to arbitration of the International Chamber of Commerce (place of arbitration shall be Brussels, language of arbitration will be English) under the Arbitration rules of the ICC. The appointing entity shall be the International Court of Arbitration (the ‘Court’). To fulfill this role, the Court shall create a special committee (the ‘Special Committee’) consisting of the Chairman of the Court and two other members of the Court.

68.5 Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Brussels, Belgium. Language is English.

| Volume 2.1 Special Conditions - ANNEX I: Schedule of Payments |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Contract Price and the other amounts (figures) are provisional and they are used only as example amounts linked with percents |  |  |  |  |  |  |
| Contract Price | 1,000,000.00 |  |  |  |  |  |
| Milestone | 1 | 2 | 3 | 4 | 14.9* |  |
| Work progress (%) | 0% | 55% | 90% | 100% |  | Units |
|  | Payment 1 (Advance) | Payment 2 | Payment 3 | Final Payment | Payment of Retention Money |  |
| Works executed (%) | 0.00 | 55.00 | 35.00 | 10.00 |  | % of Contract Price |
| Works executed (amount) | 0.00 | 550,000.00 | 350,000.00 | 100,000.00 |  | Euro |
| Works executed - Accumulated (%) | 0.00 | 55.00 | 90.00 | 100.00 |  | % of Contract Price |
| Works executed - Accumulated (amount) | 0.00 | 550,000.00 | 900,000.00 | 1,000,000.00 |  | Euro |
| Deduction for retention (%) [ - ] | 0.00 | 10.00 | 10.00 | 10.00 |  | % of Payment |
| Deduction for retention (%) [ - ] | 0.00 | 5.50 | 3.50 | 1.00 |  | % of Contract Price |
| Deduction for retention (amount) [ - ] | 0.00 | 55,000.00 | 35,000.00 | 10,000.00 |  | Euro |
| Retention Money - Accumulated (%) | 0.00 | 5.50 | 9.00 | 10.00 | 10.00 | % of Contract Price |
| Retention Money - Accumulated (amount) | 0.00 | 55,000.00 | 90,000.00 | 100,000.00 | 0.00 | Euro |
| Deduction for Repayment of Advance (%) [ - ] | 0.00 | 50.00 | 50.00 |  |  | % of Advance |
| Deduction for Repayment of Advance (%) [ - ] | 0.00 | 10.00 | 10.00 |  |  | % of Contract Price |
| Deduction for Repayment of Advance (amount) [ - ] | 0.00 | 100,000.00 | 100,000.00 |  |  | Euro |
| Advance Repayment - Accumulated (%) | 0.00 | 50.00 | 100.00 |  |  | % of Advance |
| Advance Repayment - Accumulated (amount) | 0.00 | -100,000.00 | -200,000.00 |  |  | Euro |
| Due to pay (%) | 20.00 | 39.50 | 21.50 | 9.00 | 10.00 | % of Contract Price |
| Due to pay (amount) | 200,000.00 | 395,000.00 | 215,000.00 | 90,000.00 | 100,000.00 | Euro |
| Payment - Accumulated (%) | 20.00 | 59.50 | 81.00 | 90.00 | 100.00 | % of Contract Price |
| Payment - Accumulated (amount) | 200,000.00 | 595,000.00 | 810,000.00 | 900,000.00 | 1,000,000.00 | Euro |