## Table of Payments
Schedule of Payments
Milestone | 1 |  |  | 2 |  | 3 |  | 4 |  | 38324
Work progress (%) | 0% |  |  | 55% |  | 90% |  | 100% |  |  | Payment | Units
| Payment 1 (Advance) | APR | MAY | Payment 2 | JULY | Payment 3 | SEP | Final Payment | NOV | Retention Payment 1 | Retention Money
Works executed (%) | 0 |  |  | 55 |  | 35 |  | 10 |  |  |  | % of Contract Price
Works executed - Accumulated (%) | 0 |  |  | 55 |  | 90 |  | 100 |  |  |  | % of Contract Price
Deduction for retention (%) [ - ] | 0 |  |  | 10 |  | 10 |  | 10 |  |  |  | % of Payment
Deduction for retention (%) [ - ] | 0 |  |  | 5.5 |  | 3.5 |  | 1 |  | 5 | -10 | % of Contract Price
Retention Money - Accumulated (%) | 0 |  |  | 5.5 |  | 9 |  | 10 |  | 5 | 0 | % of Contract Price
Deduction for Repayment of Advance (%) [ - ] | 0 |  |  | 50 |  | 50 | [5 empty] | % of Advance
Deduction for Repayment of Advance (%) [ - ] | 0 |  |  | 0 |  | 0 | [5 empty] | % of Contract Price
Advance Repayment - Accumulated (%) | 0 |  |  | 50 |  | 100 | [5 empty] | % of Advance
Due to Pay (%) | 0 |  |  | 49.5 |  | 31.5 |  | 9 |  | 5 | 10 | % of Contract Price
Payment - Accumulated (%) | 0 |  |  | 49.5 |  | 81 |  | 90 |  | 5 | 100 | % of Contract Price
3822126
1031974.02

## Table of Payments (E)
Schedule of Payments
Contract Price and the other amounts (figures) are provisional and they are used only as example amounts linked with percents
Contract Price | 1000000
Milestone | 1 |  |  | 2 |  | 3 |  | 4 |  | 38324
Work progress (%) | 0% |  |  | 55% |  | 90% |  | 100% |  |  |  |  | Units
| Payment 1 (Advance) | APR | MAY | Payment 2 * | JULY | Payment 3 | SEP | Final Payment | NOV | Retention Payment 1 | Payment of Retention Money | Retention money 2nd payment
Works executed (%) | 0 |  |  | 55 |  | 35 |  | 10 |  |  |  |  | % of Contract Price
Works executed (amount) | 0 |  |  | 550000 |  | 350000 |  | 100000 |  |  |  |  | Euro
Works executed - Accumulated (%) | 0 |  |  | 55 |  | 90 |  | 100 |  |  |  |  | % of Contract Price
Works executed - Accumulated (amount) | 0 |  |  | 550000 |  | 900000 |  | 1000000 |  |  |  |  | Euro
Deduction for retention (%) [ - ] | 0 |  |  | 10 |  | 10 |  | 10 |  |  |  |  | % of Payment
Deduction for retention (%) [ - ] | 0 |  |  | 5.5 |  | 3.5 |  | 1 |  | 5 |  |  | % of Contract Price
Deduction for retention (amount) [ - ] | 0 |  |  | 55000 |  | 35000 |  | 10000 |  | 50000 |  |  | Euro
Retention Money - Accumulated (%) | 0 |  |  | 5.5 |  | 9 |  | 10 |  | 5 | 10 | 0 | % of Contract Price
Retention Money - Accumulated (amount) | 0 |  |  | 55000 |  | 90000 |  | 100000 |  | 50000 | 0 |  | Euro
Deduction for Repayment of Advance (%) [ - ] | 0 |  |  | 50 |  | 50 | [6 empty] | % of Advance
Deduction for Repayment of Advance (%) [ - ] | 0 |  |  | 10 |  | 10 | [6 empty] | % of Contract Price
Deduction for Repayment of Advance (amount) [ - ] | 0 |  |  | 100000 |  | 100000 | [6 empty] | Euro
Advance Repayment - Accumulated (%) | 0 |  |  | 50 |  | 100 | [6 empty] | % of Advance
Advance Repayment - Accumulated (amount) | 0 |  |  | -100000 |  | -200000 | [6 empty] | Euro
Due to pay (%) | 20 |  |  | 39.5 |  | 21.5 |  | 9 |  | 5 | 10 | 0 | % of Contract Price
Due to pay (amount) | 200000 |  |  | 395000 |  | 215000 |  | 90000 |  | 50000 | 100000 | 0 | Euro
Payment - Accumulated (%) | 20 |  |  | 59.5 |  | 81 |  | 90 |  | 5 | 100 | 100 | % of Contract Price
Payment - Accumulated (amount) | 200000 |  |  | 595000 |  | 810000 |  | 900000 |  | 50000 | 1000000 | 1000000 | Euro

## Payment Procedure
Payment Procedure (Lot 1 & 2)
Installment Number | Works Completed % | Statement Date | Payment Certificate Date* | Payment Date*
| by |  | by | by
| Contractor |  | Engineer | Beneficiary
1 | 0
2 | 55
3 | 90
4 | 100
Payment | Retention Money
All dates are provisional and they are used as example for Payment Procedure
Final Statement