VOLUME 2

# SECTION 3:
SPECIAL CONDITIONS

- CONTENTS

- Article 1: 	Definitions

1.5 ‘“Beneficiary” means the beneficiary of the contracted works. This is the person named as such in the Appendix to Tender and the legal successors in title to this person.

- Article 2: 	Law and language of the contract

2.1	Community law is the law which applies to the contract, complemented, where necessary, by Belgian law.

2.3	The language used shall be English.

- Article 3: 	Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

(a) the contract,

(b) the Special Conditions,

(c) the General Conditions,

(d) the technical specifications,

(e) the design documentation (drawings),

(f) the price breakdown,

(g) the tender with the appendix,

(h) any other document forming part of the contract.

- Article 4:	Communications

For the Contracting Authority

| Name: | Delegation of the European Commission to the Republic of Serbia |
| --- | --- |
| Address: | GTC 19 Avenue Building, Vladimira Popovica 40, 11070 Belgrade, Serbia |
| Telephone: | Tel.: +381 11 3083 200 |
| Fax: | Fax.: +381 11 3083 201 |
| e-mail: | Delegation-serbia@ec.europa.eu |

For the Contracting Authority’s Representative

| Name: | Mr Josep Lloveras, Head of Delegation |
| --- | --- |
| Address: | GTC 19 Avenue Building, Vladimira Popovica 40, 11070 Belgrade, Serbia |
| Telephone: | Tel.: +381 11 3083 200 |
| Fax: | Fax.: +381 11 3083 201 |
| e-mail: | Delegation-serbia@ec.europa.eu |

For the Beneficiary

EPS

| Name: | Dragomir Markovic |
| --- | --- |
| Address: | Serbia, 11000 Belgrade, Balkanska 13 |
| Telephone: | + 381 11 620-921 |
| Fax: | + 381 11 629-489 |
| e-mail: | dragomir.markovic@eps.rs |

TENT

| Name: | Biljanovski Djordji |
| --- | --- |
| Address: | Serbia, 11500 Obrenovac, TENT Bogoljuba Urosevica - Crnog 44 |
| Telephone: | + 381 11 8755 003 |
| Fax: | + 381 11 8755 500 |
| e-mail: | djordji.biljanovski@tent.rs |

For the Supervisor:

| Name: |  |
| --- | --- |
| Address: |  |
| Telephone: |  |
| Fax: |  |
| e-mail: |  |

For the Works Contractor.

| Name: |  |
| --- | --- |
| Address: |  |
| Telephone: |  |
| Fax: |  |
| e-mail: |  |

4.1	All communications shall be written (hard copy) and delivered either by:

1) Safe hand to the office of the other party

2) Private courier service

3) E-mail

4) Fax

Where signed documents are transmitted electronically they shall be confirmed by  delivery of hard copy with the original signatures within one week.

- Article 5:	Supervisor and Supervisor's representative

5.2 	Office accommodation for the Supervisor will be provided by the Beneficiary, EPS.

5.3 	The Supervisor acts for the Contracting Authority. He has no authority to relieve either party of any duties, obligations or responsibilities under the Contract. Any approval, check, certificate, consent, examination, inspection, instruction, notice, proposal, request, test, or similar act by the Supervisor (including absence or disapproval) shall not relieve the Contractor from any responsibility he has under the Contract, including the responsibility for errors, omissions, discrepancies and non-compliances.

Any failure to disapprove any work, plant or materials shall not constitute approval, and shall therefore not prejudice the right of the Supervisor to reject the work, plant or materials.

The Supervisor may issue to the Contractor (at any time) instructions which may be necessary for the execution of the works and the remedying of any defects, all in accordance with the Contract. The Contractor shall only take instructions from the Supervisor. If an instruction constitutes a modification, Article 37 of General Conditions shall apply.

The Supervisor shall consult with each party in an endeavour to reach agreement. If agreement is not achieved, the Supervisor shall make a fair determination in accordance with the Contract, taking due regard of all relevant circumstances.

During the design stage Supervisor shall be entitled to perform checks on Contractor progress as well as compliance with Technical Specification. These checks shall be performed at least once in two weeks and Supervisor shall have right to ask for clarification, to approve or reject proposed design solution. Except for changes that are result of additional Beneficiary’s Requests approved by the Supervisor, Contractor shall not be entitled to any additional costs and/or extension of time, which may occur as result of clarification or rejection of the part or whole of design.

The Beneficiary shall monitor the Project according to Volume 3 and  the approved Time Shedule.

5.4 	Administrative orders issued by the Supervisor shall be dated, numbered and entered in a register. The Supervisor shall send them electronically (by email) to representatives of the Contractor, of the Beneficiary and of the Contracting Authority. Hard copies shall be delivered by hand to representatives of the Contractor and of the Beneficiary, and where appropriate, also to the representative of the Contracting Authority.

- Article 7:	Sub-contracting

Subcontracting is allowed up to 50% of the value of the Contract Works.

- Article 8:	Documents to be provided

On the basis of the

- Inspection Report of the EsP equipment at TENT A Power Plant, Unit A6, and

- Inspection Report of the EsP equipment at TENT B Power Plant, Unit B2,

provided by the Contracting Authority,

- Data collection at site,

- Ash resistivity measurement,

- Particles size measurement,

done by the Contractor on site, he shall produce

- Flue Gas Computational fluid Model (CFD),

- Basic Design, and

- Detailed Design.

The Contractor's Documents shall comprise the technical documents specified in the Technical Requirements, documents required to satisfy all regulatory approvals.

The Contractor shall prepare all Contractors’ Documents, and shall also prepare any other documents necessary to instruct the Contractor's Personnel. The Beneficiary's Personnel shall have the right to inspect the preparation of all these documents, wherever they are being prepared.

8.2  Unless it is necessary for the purposes of the contract, the drawings, specifications and

other documents provided by the Contracting Authority / Beneficiary shall not be used or

communicated to a third party by the Contractor without the prior consent of the

Supervisor.

- Article 9:	Access to the site

9.1     Access to site to the Contractor:

The Beneficiary shall, in due time and in conformity with the progress of the works, place the site and access thereto at the disposal of the Contractor in accordance with the programme of implementation of tasks referred to in these General Conditions. The Contractor shall afford all reasonable opportunities to other persons concerned for carrying out their work as set out in the Special Conditions or as required by administrative orders.

Period of access to the site will be:

(A6) - 01.05.2010. -30.11.2011.

(B2) - 01.04.2011. - 31.07.2012.

9.3. The Contractor shall preserve any premises placed at his disposal in a good state while he

is in occupation and shall, if so required by the Contracting Authority, Beneficiary or the Supervisor, restore them to their original state on completion of the contract, taking into account

normal wear and tear.

9.5 The Contractor’s attention is drawn to the fact that there is a Head of Delegation of the European Commission in the state of the Contracting Authority. The Contractor is bound to give the Head of Delegation/his representatives free access to its sites, factories, workshops, etc., and generally assist the Head of Delegation/his representatives, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the Head of Delegation.

All correspondence between the Contractor and the Contracting Authority or project Supervisor must be copied, for information, to the Head of Delegation/his representatives of the European Commission at the following official address:

Delegation of the European Commission to the Republic of Serbia

GTC 19 Avenue Building

Vladimira Popovica 40

11070 Belgrade

Serbia

Tel.: +381 11 3083 200

Fax.: +381 11 3083 201

Article 10: 	Assistance with local regulations

10.1 The Contractor may request the assistance of the Contracting Authority / Beneficiary in obtaining copies of laws, regulations and information on local customs, orders or by-laws of the

country where the works are located, which may affect the Contractor in the performance

of his obligations under the contract. The Contracting Authority / Beneficiary may provide the

assistance requested to the Contractor at the Contractor's cost.

Article 12:	General obligations of the Contractor

12.8	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: http://ec.europa.eu/europeaid/work/visibility/index_en.htm.

12a: 	Design and build contracts

For design and build contracts only, the Contractor shall carry out, and assume responsibility

for, the design of the works with the help of experienced designers satisfying the criteria laid

down by the Contracting Authority. He shall draw up the requisite technical documents

according to the provisions laid down in the Special Conditions and technical specifications.

These documents must be submitted to the Supervisor and Beneficiary for approval, in accordance with the Special Conditions, and may be corrected at the Contractor's expense to satisfy the Contracting Authority's contractual requirements and eliminate errors, omissions, ambiguities, inconsistencies and other drafting defects. The Contractor shall train the Beneficiary's personnel and deliver and update the set of detailed

12b:	Design and build contracts

The Contractor will produce and be responsible for the Basic Design, the Detailed Design and Flue Gas Computational fluid Model (CFD), with all necessary drawings and calculations, on the basis of the Functional and performance specifications as presented in the Volume 3 of the Tender Dossier (, Technical Requirements), Volume 4 (Breakdown of the Overall Price) and Volume 5 (Design Documents, including Drawings), and on the basis on his own measurements on site. All additional necessary information for this purpose, the Contractor will get from the Beneficiary.

Design(s) shall be prepared by qualified licensed designers who are engineers or other professionals who comply with the criteria stated in the Technical Requirements. Unless otherwise stated in the Contract, the Contractor shall submit to the Supervisor for consent the name and particulars of each proposed designer and design Subcontractor.

The Contractor warrants that he, his designers and design Subcontractors have the experience and capability necessary for the design. The Contractor undertakes that the designers shall be available to attend discussions with the Supervisor at all reasonable times, until the expiry date of the relevant Defects Liability Period.

- The CFD, the Basic Design, and the Detailed Design (in English language) will be submitted to the Supervisor for his inspection and to the Beneficiary. The official inspection and approval of the Detailed Design shall be performed as per the Construction Law of the Republic of Serbia and shall be organized by the Beneficiary.

The Beneficiary will obtain all necessary permits for execution of works, and is responsible for necessary expropriations and reallocation of utilities.

- Officially approved Detailed Design, by authorities in charge, will be the basis for implementation of works.

- Contractor will produce necessary workshop drawings and As Built Drawings.

Article 14:	Staff

14.1 	Add the following paragraph to the article 14.1: All relevant employees must possess the necessary professional licences as required by the Construction law and other relevant legal provisions. Project Manager should have at least 10 years of professional experience, and other Key personnel should have at least 5 years of professional experience.

14.3  Working hours

The Beneficiary will enable access to the site 7 days in the week, 24 hours, for the whole duration of the works.

No work shall be carried out on the Site on locally recognised days of rest, or outside the normal working hours, unless:

the Supervisor gives consent, or  the work is unavoidable, or necessary for the protection of life or property or for the safety of the Works, in which case the Contractor shall immediately advise the Supervisor.

- Article 15:	Performance guarantee

15.1	The amount of the performance guarantee covering liquidated damages for the performance of the works shall be 10% of the amount of the Contract and any addenda thereto.

- Article 16:	Insurance

The Sub-article 16.1 of the GC changes and reads 16.1. The Contractor shall insure in the joint names of the Contracting Authority, Beneficiary and himself against loss or damage for which he is liable under the contract. Such insurance shall, unless the Special Conditions provide otherwise, cover:

(a) the works, together with materials and plant for incorporation therein, to the full

replacement cost against all loss or damage from whatever cause arising other than

from force majeure or risks attributable under the contract to the Contracting

Authority;

(b) an additional sum of 15% of such replacement cost, or as may be specified in the

Special Conditions, to cover any additional costs of and incidental to the

rectification of loss or damage including professional fees and the cost of

demolishing and removing any part of the works and of removing debris of

whatever nature;

(c) the Contractor's equipment and other things brought onto the site by the

Contractor, for a sum sufficient to provide their replacement at the site.

16.7	The amount of insurance for design is 10% of the Contract amount..

- Article 17:	Programme of implementation of tasks

There are no specific requirements of the programme of implementation of tasks.

- Article 19:	Contractor's drawings

  - Add the following paragraph to the article 19.1:

The Contractor shall prepare, and keep up-to-date, a complete set of "as-built" records of the execution of the Works, showing the exact as-built locations, sizes and details of the work as executed. These records shall be kept on the Site and shall be used exclusively for the purposes of this Sub-Clause. Two copies shall be supplied to the Supervisor prior to the commencement of the Tests on Completion.

In addition, the Contractor shall supply to the Engineer as-built drawings of the Works, showing all Works as executed, and submit them to the Supervisor for review under. The Contractor shall obtain the consent of the Supervisor as to their size, the referencing system, and other relevant details.

Prior to the issue of any Provisional Acceptance, the Contractor shall supply to the Supervisor the specified numbers and types of copies of the relevant as-built drawings, in accordance with the Technical Requirements. The Works shall not be considered to be completed for the purposes of acceptance under Articles 57 to 62 of the General Conditions until the Supervisor has received these documents.

19.7 Before provisional acceptance of the works, the Contractor shall supply operation and

maintenance manuals together with drawings, which shall be in such detail as will enable

the Beneficiary to operate, maintain, adjust and repair all parts of the works.

The language of the manuals and drawings will be English and Serbian. The works shall not be considered to be completed for the purpose of provisional acceptance until such manuals and drawings have been supplied to the Beneficiary.

- Article 20:	Sufficiency of tender prices

Tender prices must cover all necessary design and build activities. No extension of contract is possible.

- Article 21:	Exceptional risks

There are no exceptional risks other than specified in the General Conditions.

- Article 22: 	Safety on sites

22.1 The Contractor shall have the right to forbid access to the site to any person not involved

in the performance of the contract, with the exception of persons authorized by the Beneficiary,

Supervisor or the Contracting Authority.

22.2 The Contractor shall ensure the safety on sites during the whole period of execution and

shall be responsible for taking the necessary steps, in the interests of his employees,

agents of the Contracting Authority, Beneficiary and third parties, to prevent any loss or accident

which may result from carrying out the works.

Article 23: 	Safeguarding adjacent properties

23.2 The Contractor shall indemnify the Contracting Authority and the Beneficiary against the financial consequences of all claims by neighbouring landowners or residents to the extent that the

Contractor is liable and to the extent that the damage to adjacent properties is not the

result of a hazard created through the design or method of construction imposed by the

Contracting Authority, beneficiary or the Supervisor upon the Contractor.

Article 24:	Interference with traffic

24.1	There are no interferences on the communication traffic.

24.2	Contractor will have to take necessary measures to secure the transportation of heavy loads and big size loads on and around the site.

- the Contractor shall (as between the Parties) be responsible for any maintenance which may be required for his use of access routes;

- the Contractor shall provide all necessary signs or directions along access routes, and shall obtain any permission which may be required from the relevant authorities for his use of routes, signs and directions;

- the Contracting Authority and the Beneficiary shall not be responsible for any claims which may arise from the use or otherwise of any access route,

- the Contracting Authority and the Beneficiary do not guarantee the suitability or availability of particular access routes, and

- Costs due to non-suitability or non-availability, for the use required by the Contractor, of access routes shall be borne by the Contractor.

For the Transport of Goods:

- the Contractor shall give the Supervisor not less than 7 days' notice of the date on which any Plant or a major item of other Goods will be delivered to the Site;

- the Contractor shall be responsible for packing, loading, transporting, receiving, unloading, storing and protecting all Goods and other things required for the Works; and

- the Contractor shall indemnify and hold the Contracting Authority and the Beneficiary harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from the transport of Goods, and shall negotiate and pay all claims arising from their transport.

Article 25: 	Cables and conduits

25.3 Where the presence of cables, conduits and installations has not been specified in the contract but is revealed by bench-marks and references, the Contractor shall be under a general duty of care and similar obligations regarding preservation, removal and replacement to those set out above. In this case, the Beneficiary shall compensate him for expenditure, to the extent that such work is necessary for the execution of the contract.

25.4 However, the obligations to remove and replace cables, conduits and installations and the

expenditure resulting therefrom shall not be the responsibility of the Contractor if the Contracting Authority decides to accept that responsibility. The same shall apply where this obligation and the expenditure resulting therefrom devolve upon another specialist administration or an agent.

- Article 27:	Demolished materials

27.1	No demolition materials will become the property of the Contracting Authority. Should some materials be of interest to the Beneficiary, they will become their property, like metallic scrap.

27.3  Irrespective of the use to which the Beneficiary intends to put the materials or articles, in respect of which he reserves the right of ownership, all costs incurred in transporting and storing them and all warehouse charges at the place indicated by the Supervisor shall be borne by the Contractor for any carriage not exceeding 100 meters.

    - The Contractor will remove demolition materials as per the tables in Volume 4: Table 4.1.2.a and 4.1.2.b, except for the items under the responsibility of the Beneficiary.

- Article 29:	Temporary works

  - Should the Contractor need any additional information or drawings apart from those being part of the Tender Dossier, he will put his request to the Beneficiary. Final decision will be on the side of the Supervisor. Particular temporary works to be performed by the Beneficiary are specified in the tables in Volume 4: Table 4.1.2.a and 4.1.2.b.

- Article 30:	Soil studies

  - No special soil studies are needed apart from what is specified in the Tender Dossier.

Article 31: 	Overlapping contracts

31.1 The Contractor shall, in accordance with the requirements of the Supervisor, afford all reasonable opportunities for carrying out their work to any other Contractors employed by the Beneficiary and their workmen, to the workmen of the Beneficiary and of any other public authorities who may be employed on or near the site in the execution of any work not included in the contract, or of any contract which the Beneficiary may enter into in connection with, or ancillary to, the works.

31.2 If, however, the Contractor, on the written request of the Supervisor, makes available to

any such Contractor, or public authority, or to the Beneficiary, any roads or ways for the maintenance of which the Contractor is responsible, or permits the use by any such other persons of the Contractor's temporary works, scaffolding or other equipment on the site, or provides any other service of whatsoever nature, which was not provided for in the contract, the Beneficiary shall pay to the Contractor in respect of such use or service, such sums and/or grant such extension of time, as shall, in the opinion of the Supervisor, be reasonable.

- Article 34:	Period of implementation of tasks

The identified date for outage by the Beneficiary for project implementation is:

Unit A6: from 01.06.2010 to 31.10.2010,

Unit B2: from 01.05.2011. to 31.07.2011.

- Article 35: 	Extension of the period of implementation of tasks

35.1 The Contractor may request an extension to the period of implementation of tasks if he is

or will be delayed in completing the contract by any of the following causes:

(a) exceptional weather conditions in the State of the Beneficiary;

(b) artificial obstructions or physical conditions which could not reasonably have been

foreseen by an experienced Contractor;

(c) administrative orders affecting the date of completion other than those arising from

the Contractor's default;

(d) failure of the Contracting Authority or Beneficiary to fulfill his obligations under the contract;

(e) any suspension of the works which is not due to the Contractor's default;

(f) force majeure;

(g) any other causes referred

35.3 Within 30 days from receipt of the Contractor's detailed particulars of the request, the

Supervisor shall, by written notice to the Contractor after due consultation with the

Contracting Authority and, where appropriate, the Contractor, grant such extension of the

period of implementation of tasks as may be justified, either prospectively or

retrospectively, or inform the Contractor that he is not entitled to an extension.

- Article 36:	Delays in implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10% of the contract price or, if the contract is subdivided into phases, 10% of the price of the phase concerned.

37.4. Following the receipt of the Contractor's submission referred to in Article 37 (3), the

Supervisor shall, after due consultation with the Contracting Authority, Beneficiary and, where

appropriate, the Contractor, decide as soon as possible whether or not the variation shall

be carried out. If the Supervisor decides that the modification shall be carried out he shall

issue the administrative order stating that the modification shall be carried out at the

prices and under the conditions given in the Contractor's submission referred to in Article

37 (3) or as modified by the Supervisor in accordance with Article 37 (5).

37.7. Where on provisional acceptance an increase or reduction in the total value of the works

resulting from an administrative order, or from some other circumstance which is not

caused by the Contractor's default, exceeds 15% of the initial contract price (or as

modified by addendum) , the Supervisor shall, after consultation with the Contracting

Authority, Beneficiary and the Contractor determine any additions to or reduction from the contract

price as a consequence of the application of Article 37 (5). The sum so determined shall

be based on the amount by which the increase or decrease in value of the works exceeds

15%. The sum shall be notified by the Supervisor to the Contracting Authority and the

Contractor and the contract price adjusted accordingly.

37.8. Contract modifications not covered by an administrative order must be formalised

through an addendum to the contract signed by all parties. Changes of address or bank

account may simply be notified in writing by the Contractor to the Contracting Authority and the Beneficiary.

All contract modifications have to respect the general principles defined in the Practical

Guide to contract procedures for EC external actions.

Article 38: 	Suspension

38.2. During the period of suspension, the Contractor shall take such protective measures as

may be necessary to safeguard the works, plant, equipment and site against any

deterioration, loss or damage. Additional expenses incurred in connection with such

protective measures shall be added to the contract price, unless such suspension is:

(a) otherwise provided for in the contract; or

(b) necessary by reason of some default of the Contractor; or

(c) necessary by reason of normal climatic conditions on site; or

(d) necessary for the safety or the proper execution of the works or any part thereof

insofar as such necessity does not arise from any act or default by the Supervisor or

the Contracting Authority, Beneficary or from any of the exceptional risks referred to in Article

21.

38.4. The Supervisor, after consultation with the Contracting Authority, Beneficiary and the Contractor, shall determine such extra payment and/or extension of the period of performance to be

made to the Contractor in respect of such claim as shall, in the opinion of the Supervisor,

be fair and reasonable.

- Article 39:	Work register

39.1	Work register is required, and practical details will be specified in the Project Manual provided by the Supervisor subject to approval by the Contracting Authority and the Beneficiary.

39.2	The technical rules for drawing up the statements will be specified in the Project Manual.

- Article 40:	Origin and quality of works and materials

## 40.1	All supplies and material to be incorporated in or required for the works must originate in a Member States of the European Union or in a country or territory of the regions covered and/or authorised by the specific instruments applicable to the IPA 2007 programme under which the contract is financed. For these purposes, "origin" means the place where the materials and/or equipment are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods shall be determined according to the rules laid down in the Community Customs Code or the international agreements to which the country concerned is a signatory.

There are no derogations from the rules of origin.

When importing goods, any change in the specified origin must have been pointed out to the project Supervisor and subject to his approval.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*) the requirements specified in Volume 3 (Technical Requirements).

(*) the specifications as in Volume 5.

40.3	No preliminary technical acceptance is necessary.

- Article 41:	Inspection and testing

The Beneficiary's Personnel shall at all reasonable times:

- have full access to all parts of the Site and to all places from which natural Materials are being obtained, and

- during production, manufacture and construction (at the Site and elsewhere), be entitled to examine, inspect, measure and test the materials and workmanship, and to check the progress of manufacture of Plant and production and manufacture of Materials, on the basis of approved QA & QP.

The Contractor shall give the Beneficiary's Personnel full opportunity to carry out these activities, including providing access, facilities, permissions and safety equipment. No such activity shall relieve the Contractor from any obligation or responsibility.

The following shall apply to all tests specified in the Contract, other than the Tests on Completion:

The Contractor shall provide all apparatus, assistance, documents and other information, electricity, equipment, fuel, consumables, instruments, labour, materials, and suitably qualified and experienced staff, as are necessary to carry out the specified tests efficiently. The Contractor shall agree, with the Supervisor, the time and place for the specified testing of any Plant, Materials and other parts of the Works.

The Supervisor may, under Article 37 [Modifications], vary the location or details of specified tests, or instruct the Contractor to carry out additional tests. If these varied or additional tests show that the tested Plant, Materials or workmanship is not in accordance with the Contract, the cost of carrying out this Modification shall be borne by the Contractor, notwithstanding other provisions of the Contract.

The Supervisor shall give the Contractor not less than 24 hours' notice of the Supervisor 's intention to attend the tests. If the Supervisor does not attend at the time and place agreed, the Contractor may proceed with the tests, unless otherwise instructed by the Supervisor, and the tests shall then be deemed to have been made in the Supervisor 's presence.

Article 42: 	Rejection

42.4 The Contractor shall with all speed and at his expense make good the defects so specified.

If the Contractor does not comply with such order, the Contracting Authority shall be

entitled to employ other persons to carry out the same and all expenses consequent

thereon or incidental thereto may be deducted by the Contracting Authority from any

monies due or which may become due to the Contractor.

- Article 43:	Ownership of plant and materials

43.2	All equipment, temporary works, plant and materials on site owned by the Contractor or by any company in which the Contractor has a controlling interest shall, for the duration of the execution of the works, be made subject to a lien in favour of the Contracting Authority.

43.5  Upon termination of the contract before completion of the works, the Contractor shall

deliver to the Beneficiary any plant, temporary works, equipment or materials

the property in which has vested in the Contracting Authority or been made subject to a

lien by virtue of Article 43 (2). If he fails to do so, the Contracting Authority may take

such appropriate action as it deems fit in order to obtain possession of such plant,

temporary works, equipment and materials and recover the cost of so doing from the

Contractor.

- Article 44:	General principles for payments

44.1	Payments shall be made in euro.

44.2	Where invoices are presented to the Contracting Authority, the Contractor shall inform the Commission of the European Communities thereof by sending a copy of the correspondence to  Delegation of the European Commission to the Republic of Serbia, F&C Section

GTC 19 Avenue Building

Vladimira Popovica 40

11070 Belgrade

Serbia

44.3	By derogation the payment to the Contractor of the amounts due under each of the interim payment certificates and the final statement of account issued by the Supervisor shall be made by the Contracting Authority within 45 days.

- Article 45: 	Provisional price contracts

45.2 The Contractor shall supply such information as the Contracting Authority or the

Supervisor may reasonably require in respect of any matter relating to the contract for the

purpose of the calculation. Where agreement cannot be reached on the valuation of the

works, the amounts payable shall be determined by the Supervisor.

- Article 46:	Pre-financing

46.(1) and (2)	Pre-financing shall be granted to the Contractor, at his request, for operations connected with the implementation of the tasks, in the cases if he affords proof of the conclusion of a contract for the purchase or order of materials, plant, equipment, machines and tools, necessary for the execution of the contract, and of any other substantial prior expenses such as the acquisition of patents or study costs.

The pre-financing shall be 20 % of the contract price.

In order to obtain pre-financing payment, the Contractor must forward to the Supervisor the payment request and the performance guarantee in accordance with article 15. The Contractor must provide a financial guarantee for the full amount of the pre-financing payment.

46.8	The repayment of the pre-financing shall take the form of deductions based on claims as per the Annex I: Schedule of payments.

- Article 47:	Retention monies

47.1	When the Final Acceptance Certificate has been issued for the Works, half of the Retention Money shall be certified by the Supervisor for payment to the Contractor.

Promptly after the latest of the expiry dates of the Defects Liability Periods, the outstanding balance of the Retention Money shall be certified by the Supervisor for payment to the Contractor.

However, if any work remains to be executed under Article 61 [Defects Liability] or Article 58 [Tests on Completion], the Supervisor shall be entitled to withhold certification of the estimated cost of this work until it has been executed.

The sum to be retained from interim payments to guarantee implementation of the Contractor's obligations during the maintenance period is10% of each instalment.

- Article 48:	Price revision

  - The contract shall be at fixed prices which shall not be revised.

- Article 49:	Measurement

49.1	This is a lump-sum contract, as per the V4: BREAKDOWN OF THE OVERALL PRICE.

- Article 50:	Interim payments

50.1	Payments will be practically arranged in the following way:

| Payment Milestone | Payment Milestone Date | Delivery Milestones | Milestone Value | Milestone Value as % of Prject Cost |
| --- | --- | --- | --- | --- |
| 1 |  | Advance Payment Contract signed, bank guarantees submitted to the CA. |  | 20% |
| 2 |  | First interim payment Time Schedule, Quality Plan and Main Design approved, Acceptance Certificate issued, Key materials ordered and Overall progress of 30% achieved. |  | 55% |
| 3 |  | Second interim payment Finalized erection of mechanical equipment and all other equipment delivered on site, Overall progress of 80% achieved. |  | 90% |
| 4 |  | Final payment Final Acceptance Certificate issued. |  | 10% |

The amount certified in each Interim Payment Certificate shall be paid by the Contracting Authority against presentation of the Invoice in the amount of Interim Payment Certificate confirmed by the Beneficiary and signed by the Supervisor; the original of the Interim Payment Certificate and original of Statement issued to and approved by the Supervisor.

- Article 51:	Final statement of account

51. (1) and (2)

51.1	The draft final statement of account shall be submitted at the latest at the moment of the Contractor's application for the provisional acceptance certificate.

51.2	The Supervisor shall prepare and sign the final statement of account within 30 days from the issue of the certificate of final acceptance referred to in article 62.

51.3 The Supervisor shall issue to the Contracting Authority or to its duly authorized representative, to the Beneficiary and to the Contractor, the final statement of account showing the final amount to which the Contractor is entitled under the contract. The Contracting Authority or its duly authorized representative and the Contractor shall sign the final statement of account as an acknowledgement of the full and final value of the work implemented under the contract and shall promptly submit a signed copy to the Supervisor. However, the final statement of account shall not include amounts in dispute which are the subject of negotiations, conciliation, arbitration or litigation.

- Article 53:	Delayed payments

53.1	Once the deadline laid down in Article 44.3 of the General Conditions has expired, the Contractor shall receive late-payment interest:

-	at the rate applied by the European Central Bank to its main refinancing transactions in euro where payments are in euro,

-	at the rediscount rate applied by the central bank of the beneficiary country if payments are in the currency of that country,

on the first day of the month in which the deadline expired, plus three and a half percentage points. The late-payment interest shall apply to the time which elapses between the date of the payment deadline, and the date on which the Contracting Authority’s account is debited. By way of exception, when the interest calculated in accordance with this provision is lower than or equal to EUR 200, it shall be paid to the Contractor only upon a demand submitted within two months of receiving late payment. The Member States are not entitled to late-payment interest]

- Article 55: Claims for additional payment

55.2. When the Supervisor has received the full and detailed particulars of the Contractor's

claim that he requires, he shall, without prejudice to Article 21 (4), after due consultation

with the Contracting Authority, Beneficiary and, where appropriate, the Contractor, determine whether the Contractor is entitled to additional payment and notify the parties accordingly.

- Article 59:	Partial acceptance

59.1. The Beneficiary may make use of the various structures, parts of structures or sections of the works forming part of the contract as and when they are completed. Any taking over of the structures, parts of structures or sections of the works by the Beneficiary shall be preceded by their partial provisional acceptance. However, works may in cases of urgency be taken over prior to acceptance provided an inventory of outstanding work is drawn up by the Supervisor and agreed to by the Contractor and the Supervisor beforehand. Once the Beneficiary has taken possession of a structure, a part thereof or section of the works, the Contractor shall no longer be required to make good any damage resulting otherwise than from faulty construction or workmanship.

59.3	The maintenance period begins after the date of Final Acceptance Certificate.

- Article 60:	Provisional acceptance

60.1. The works shall be taken over by the Beneficary when they have satisfactorily

passed the tests on completion and a certificate of provisional acceptance has been issued

or is deemed to have been issued.

60.5. Immediately after provisional acceptance, the Beneficiary may make use of all

- the works as completed.

- Article 61:	Defects liability

- The duration of the Defects Liability period is 365 days.

| Reliability Run The total Contract value will decrease by the percentage specified for every day or part of a day during the Defects Liability Period, during which Units A6 / B2 are out of operation as a direct result of a fault of the Upgrated Electrostatic Precipitation System Main function. | 0.2% of Total Contact Price per day, up to 10%. |
| --- | --- |

61.1	As stated in the glossary of terms in general annexes, the defects liability period is defined as the period stated in the contract immediately following the date of provisional acceptance, during which the Contractor is required to complete the works and to remedy defects or faults as instructed by the Supervisor. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.3 If any such defect appears or such damage occurs, during the period referred to in Article

61 (1), the Contracting Authority or the Supervisor shall notify the Contractor. If the

Contractor fails to remedy a defect or damage within the time limit stipulated in the

notification, the Contracting Authority may:

(a) authorize the Beneficiary to carry out the works himself, or employ someone else to carry out the works, at the Contractor's risk and cost, in which case the costs incurred by the Beneficiary shall be deducted by the Contracting Authority from monies due to or from guarantees held against, the Contractor, or from both; or

(b) terminate the contract.

61.4 If the defect or damage is such that the Beneficiary has been deprived substantially of the whole or a part of the benefit of the works, the Beneficairy through the Contracting Authority shall, without prejudice to any other remedy, be entitled to recover all sums paid in respect of the parts of the works concerned together with the cost of dismantling such parts and clearing the site.

61.5 In case of emergency, where the Contractor cannot be reached immediately or, having

been reached, is unable to take the measures required, the Beneficiary or the Supervisor may have the work carried out at the expense of the Contractor. The Beneficiary or the Supervisor shall as soon as practicable inform the Contractor and the Contracting Authority of the action taken.

61.6 	The defects liability work necessitated by normal wear and tear is to be carried out by the Contractor.

- Article 68:	Dispute settlement

The Sub-article 68.3 of the GC changes and reads: In the absence of an amicable settlement, a Party may notify the other Party in writing requesting a settlement through conciliation by a Dispute-settlement Committee. This Committee shall be appointed within 60 days of any party giving referral of a dispute to the Dispute-settlement Committee. The Committee shall comprise of 1 (one member) to be appointed by International Chamber of Commerce. Rules of the ICC apply, and the language is English.

The other Party shall respond to this request for conciliation within 30 days. Unless the Parties agree otherwise, the maximum time period laid down for reaching a settlement through conciliation shall be 120 days from the notification requesting such a procedure. Should a Party not agree to the other Party's request for conciliation, should a Party not respond in time to that request or should no settlement be reached within the maximum time period, the conciliation procedure is considered to

have failed.

68.4	If the conciliation procedure fails, each Party may refer the dispute to arbitration of the International Chamber of Commerce (place of arbitration shall be Brussels, language of arbitration will be English) under the Arbitration rules of the ICC. The appointing entity shall be the International Court of Arbitration (the ‘Court’). To fulfill this role, the Court shall create a special committee (the ‘Special Committee’) consisting of the Chairman of the Court and two other members of the Court.

68.5 Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Brussels, Belgium. Language is English.

| Volume 2.1 Special Conditions - ANNEX I: Schedule of Payments |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Contract Price and the other amounts (figures) are provisional and they are used only as example amounts linked with percents |  |  |  |  |  |  |
| Contract Price | 1,000,000.00 |  |  |  |  |  |
| Milestone | 1 | 2 | 3 | 4 | 14.9* |  |
| Work progress (%) | 0% | 55% | 90% | 100% |  | Units |
|  | Payment 1 (Advance) | Payment 2 | Payment 3 | Final Payment | Payment of Retention Money |  |
| Works executed (%) | 0.00 | 55.00 | 35.00 | 10.00 |  | % of Contract Price |
| Works executed (amount) | 0.00 | 550,000.00 | 350,000.00 | 100,000.00 |  | Euro |
| Works executed - Accumulated (%) | 0.00 | 55.00 | 90.00 | 100.00 |  | % of Contract Price |
| Works executed - Accumulated (amount) | 0.00 | 550,000.00 | 900,000.00 | 1,000,000.00 |  | Euro |
| Deduction for retention (%) [ - ] | 0.00 | 10.00 | 10.00 | 10.00 |  | % of Payment |
| Deduction for retention (%) [ - ] | 0.00 | 5.50 | 3.50 | 1.00 |  | % of Contract Price |
| Deduction for retention (amount) [ - ] | 0.00 | 55,000.00 | 35,000.00 | 10,000.00 |  | Euro |
| Retention Money - Accumulated (%) | 0.00 | 5.50 | 9.00 | 10.00 | 10.00 | % of Contract Price |
| Retention Money - Accumulated (amount) | 0.00 | 55,000.00 | 90,000.00 | 100,000.00 | 0.00 | Euro |
| Deduction for Repayment of Advance (%) [ - ] | 0.00 | 50.00 | 50.00 |  |  | % of Advance |
| Deduction for Repayment of Advance (%) [ - ] | 0.00 | 10.00 | 10.00 |  |  | % of Contract Price |
| Deduction for Repayment of Advance (amount) [ - ] | 0.00 | 100,000.00 | 100,000.00 |  |  | Euro |
| Advance Repayment - Accumulated (%) | 0.00 | 50.00 | 100.00 |  |  | % of Advance |
| Advance Repayment - Accumulated (amount) | 0.00 | -100,000.00 | -200,000.00 |  |  | Euro |
| Due to pay (%) | 20.00 | 39.50 | 21.50 | 9.00 | 10.00 | % of Contract Price |
| Due to pay (amount) | 200,000.00 | 395,000.00 | 215,000.00 | 90,000.00 | 100,000.00 | Euro |
| Payment - Accumulated (%) | 20.00 | 59.50 | 81.00 | 90.00 | 100.00 | % of Contract Price |
| Payment - Accumulated (amount) | 200,000.00 | 595,000.00 | 810,000.00 | 900,000.00 | 1,000,000.00 | Euro |